## materials
PO Number | Vendor | Material | Quantity | Unit Cost | Total Cost | Delivery Date | Phase
PO1001 | Graybar | MC Cable | 1000 | 0.65 | 650 | 2025-06-01 | Rough-in
PO1002 | Rexel | LED Troffers | 50 | 85 | 4250 | 2025-06-03 | Trim-out
PO1003 | Graybar | Panelboard | 2 | 1200 | 2400 | 2025-06-07 | Main Service
PO1004 | City Electric | Wire | 5000 | 0.12 | 600 | 2025-06-10 | Rough-in

## labor
Date | Employee | Hours Worked | Hourly Rate | Phase
2025-06-01 | John | 8 | 38 | Rough-in
2025-06-02 | Mike | 9 | 38 | Rough-in
2025-06-03 | Sara | 8 | 42 | Rough-in
2025-06-04 | John | 8 | 38 | Trim-out
2025-06-05 | Mike | 10 | 38 | Trim-out
2025-06-06 | Sara | 8 | 42 | Trim-out
2025-06-07 | John | 7 | 38 | Main Service

## change_orders
CO Number | Description | Date Submitted | Approved | Cost Impact | Schedule Impact (Days)
CO01 | Additional receptacles | 2025-06-03 | Yes | 1200 | 2
CO02 | Change light fixtures | 2025-06-06 | No | 0 | 0
CO03 | Add data cabling | 2025-06-08 | Yes | 850 | 1

## equipment_rentals
Rental ID | Equipment | Rental Company | Start Date | End Date | Daily Rate | Total Days | Total Cost
R001 | Scissor Lift | Sunbelt | 2025-06-02 | 2025-06-05 | 150 | 4 | 600
R002 | Conduit Bender | United Rentals | 2025-06-05 | 2025-06-07 | 60 | 3 | 180
R003 | Power Threader | Sunbelt | 2025-06-07 | 2025-06-10 | 85 | 4 | 340